## Management Summary
GB300 / TI036 Quality & Yield Analysis Report
Report Period: Oct 21, 2025 – Apr 23, 2026 ¦ Generated: 2026-04-27 ¦ Scope: TI036 (L10 + L11) + All L11 Projects
▌ KEY METRICS AT A GLANCE
TI036 L10 First Pass Yield 77.24% |  |  | TI036 L10 Failure Rate 22.76% | TI036 L11 Pass Rate 99.83% | L11 Cumulative FG 575 Racks
Total L10 Tested (TI036) 13,438 Units |  |  | Total Replace Events (L10) 1,051 Events | Workmanship Rate (L10) 1.62% (218 pcs) | All-Projects L11 Pass Rate 99.82%
Top Fail Reason (TI036 L10) CX7/CX8 Diag Fail (332, 9.09%) |  |  | Top Replace Part (L10) GPU-NVGB300-12-MAXQ (302, 28.73%) | Top L11 Replace Component GB300 L10 (332, 75.97%) | Pending Issues (Latest) 5 Active Items
▌ EXECUTIVE SUMMARY – KEY FINDINGS (5-8 Points)
# | Category | Finding / Detail
1 | ✅ Overall Status | 【IMPROVING】TI036 L10 FPY 77.24%; L11 cumulative 575/576 racks (99.83%); all-projects L11 overall 1,629/1,632 racks (99.82%). L11 is near completion and performing well.
2 | ⚠️ Top Risk: GPU Failure | GPU-NVGB300-12-MAXQ dominates L10 replacements (302 events, 28.73%), with 43 occurrences in last 7 days — consistently the #1 replacement driver. Immediate investigation and vendor escalation recommended.
3 | ⚠️ CX7/CX8 Diagnostic Failure | The single largest fail reason is "GB200 NVIDIA Manufacturer Diagnostic CX7/CX8 fail" with 332 occurrences (9.09% of all TI036 L10 records). This is a systemic issue that needs root cause analysis.
4 | 📊 L10 FR at 22.76% | Total L10 failure rate is 22.76% (3,059 / 13,438), with FPY 77.24%. This reflects in-process failures that were caught and corrected before shipping.
5 | 🔧 Workmanship Rate: 1.62% | Workmanship defects total 218 events (1.62% of tested), dominated by Component Damage – Assembly Responsibility (AS008: 114 events, 52.3%). AOM-OSFP-GB-P is the top workmanship-damaged part (24 events).
6 | 📦 L11 Replacement Driver | At rack (L11) level, GB300 L10 node replacement is the #1 driver (332 events, 75.97% of 437 total L11 replacements). Cable Cartridge (54, 12.36%) and NVSwitch (35, 8.01%) are secondary drivers.
7 | 🔍 NDF Rate Alert: AOM-SCM-GB-P 19.5% | AOM-SCM-GB-P has the highest confirmed NDF% at 19.51% (16/82), suggesting possible misdiagnosis or testing protocol issues. AOM-PDB-B3-P has 10.85% NDF rate. GPU-NVGB300-12-MAXQ NDF data marked NA.
8 | 🚨 5 Pending Items as of Apr 23 | 5 active PENDING records (4/23/2026): EGM set error, Network diagnostic fail, Auto reboot, IPMI sensor fail, Auto shutdown – all TI036. Requires immediate resolution before dispatch.
▌ PRIORITY ACTION ITEMS (Top 3 Immediate + Short/Long Term)
Priority | Action Area | Recommended Action
P1 - IMMEDIATE | GPU-NVGB300-12-MAXQ Failure Surge | Vendor escalation for GPU-NVGB300-12-MAXQ (302 total, 43 in last 7 days). Request batch quality inspection, FW compatibility check, and incoming inspection protocol.
P2 - IMMEDIATE | CX7/CX8 Diagnostic Fail Root Cause Analysis | 332 failures from GB200 NVIDIA Manufacturer Diagnostic CX7/CX8. Collaborate with NVIDIA to identify systematic firmware or hardware issue. Update test procedures.
P3 - IMMEDIATE | Clear 5 Pending TI036 Issues (Apr 23) | Resolve 5 open PENDING records (EGM error, Network diag fail, Auto reboot, IPMI sensor fail, Auto shutdown). Prevent shipping hold.
Short Term (1-4 weeks) | AOM-SCM-GB-P / AOM-PDB-B3-P NDF Investigation | High NDF rates (19.51% and 10.85%) suggest possible false failure detection. Review test criteria, improve ESD/handling procedures for AOM components.
Long Term (1-3 months) | Workmanship Reduction Program | AS008 (Component Damage – Assembly) = 52.3% of all workmanship defects. Implement rework technician certification, assembly jig improvements, and optical inspection at OSFP/GPU connector steps.

## A - L11 Update Summary
A. GB300 L11 Update Summary – All Projects
Project: TI036 (SRS-52UGB300-NVL72-TI036) ¦ Period: 2026-02-12 ~ 2026-04-23
Item | Value | Formula / Note
Status | In Progress / Active Production | L11 assembly ongoing; latest data: 2026-04-23
Cumulative Input Qty (Racks) | 576 | Total racks entered L11 assembly (New Input Q'ty cumulative)
L11 Pass Qty (Cumulative FG) | 575 | L11 Finished Goods CUMULATIVE (latest snapshot)
L11 Failed Qty | 1 | 576 input - 575 pass = 1 (PENDING status)
L11 Packed / Shipped Qty | 575 | All Finished Goods counted as packed (no separate packing tracking column found)
L11 Pass Rate | 99.83% | 575 / 576 × 100 = 99.83%
Replacement SN Failure Rate | 57.74% | 332 racks required L10 replacement / 575 racks processed (one or more L10 replaced)
Total L11 Replace Events | 437 | All REPLACE actions in TI036 rack fail records
Date Coverage | 2026-02-12 to 2026-04-23 | 54 production days / dates
▌ All Projects L11 Comparison Table
Project | Rack P/N | L11 Input | L11 Pass (FG) | L11 Fail | Pass Rate | Status
xAI_TW008 | SRS-GB300-NVL72-M4-TW008 | 600 | 600 | 0 | 100.00% | ✅ Complete
TI036 | SRS-52UGB300-NVL72-TI036 | 576 | 575 | 1 | 99.83% | 🔵 Active (1 pending)
FG001 | SRS-GB300-NVL72-M0-FG001 | 256 | 256 | 0 | 100.00% | ✅ Complete
MA023 | SRS-GB300-NVL72-M0-MA023 | 192 | 190 | 2 | 98.96% | 🔵 Active
TD004 | SRS-GB300-M1-TD004 | 8 | 8 | 0 | 100.00% | ✅ Complete
TOTAL | — | 1632 | 1629 | 3 | 99.82% | 🔵 Near Completion
Data Notes & Quality Issues Found
⚠️ TI036 Yield Rate column shows "-2" for 2026-02-25 (likely formula error; Input=0, Pass=1 from prior carryover → recalculated as N/A)
⚠️ TI036 Summary row "L11 Finished Goods CUMULATIVE" sums to 14,226 (all daily values) but actual latest is 575 — the sum is meaningless; use latest snapshot value
⚠️ "L11 Packed Qty" not tracked as a separate column in either file — using "L11 Finished Goods CUMULATIVE" as proxy for packed/ready units
⚠️ 2026/3/15-16 date range merged as single entry — treated as one production period, allocated as Sunday-Monday combined
⚠️ MA023 pass rate shows 190/192 (98.96%) — 2 remaining units may still be in process

## B - L10 FR Distribution
B. TI036 / GB300 L10 Failure Rate Distribution Analysis
▌ Key Metrics & Formulae
# | Metric | Numerator | Denominator | Result | Formula | Note
1 | L10 Total Tested (Input) | 13,438 | — | 13,438 units | SUM(Daily Testing Input) | TI036 server-level, Feb–Apr 2026
2 | L10 Cumulative Pass (FG) | 10,379 | — | 10,379 units | Latest Cumulative FG column | Last date: 2026-04-24
3 | L10 Total Failed | 3,059 | — | 3,059 units | SUM(Daily Fail Qty) | Total fails caught in test
4 | L10 Failure Rate (FR) | 3,059 (fail) | 13,438 (input) | 22.76% | Fail / Input × 100 | 3,059 / 13,438 = 22.76%
5 | L10 First Pass Yield Rate | 10,379 (pass) | 13,438 (input) | 77.24% | Cum Pass / Input × 100 | 10,379 / 13,438 = 77.24%
6 | Replacement SN Failure Rate (L11) | 332 (L10 repl) | 575 (racks) | 57.74% | L10 Replace Events / Total Racks | 332 racks needed ≥1 L10 replacement at L11
7 | Total L11 Replace Events (all parts) | 437 | 575 racks | 0.76 events/rack | Total Replace / Total Racks | Multi-part replacements in same rack counted separately
8 | Workmanship Qty | 218 | — | 218 events | TI036 Workmanship sheet count | AS-code classified events, Feb–Apr 2026
9 | Workmanship Rate | 218 (ws events) | 13,438 (input) | 1.62% | Workmanship Qty / Input × 100 | 218 / 13,438 = 1.62%
10 | L10 FPY (simplified check) | 10,379 | 10,379+3,059=13,438 | 77.24% | Pass / (Pass+Fail) × 100 | Consistent — numbers reconcile correctly
▌ All Products L10 FR Comparison (from Fail Information)
Product | Server P/N | Total Records | REPLACE | REPAIR | FIX | PENDING | Notes
TI036 | PIO-121GL-NB3-LC5-TI036 | 3,653 | 1,253 | 2,042 | 706 | 5 | PRIMARY FOCUS
TW008 | PIO-121GL-NB3-LC5-TW008 | 4,949 | 2,463 | 1,902 | 1,168 | 0
FG001 | ARS-121GL-NB3-LCC-FG001 | 1,656 | 671 | 684 | 602 | 0
MA023 | ARS-121GL-NB3-LCC-R1 | 1,689 | 701 | 762 | 452 | 0
TD004 | ARS-121GL-NB3-LC1-TD004 | 64 | 24 | 25 | 30 | 0

## C - Pending Issue TOP10
C. TI036 / GB300 L10 Pending Issue Pareto – TOP 10 Defect Reasons
Scope: TI036 (PIO-121GL-NB3-LC5-TI036) ¦ Total Records: 3,653 ¦ Period: Feb ~ Apr 2026
Rank | Defect Reason (Fail Reason) | Fail Q'ty | Weight % | Category
#1 | GB200 NVIDIA Manufacturer Diagnostic CX7 / CX8 fail | 332 | 9.09% | NIC / Diagnostic
#2 | GB200 Firmware flash Power failed on turn ON after 3 appempts | 70 | 1.92% | Firmware
#3 | GPU Manufacturer Diagnostic - [FAILED] | 69 | 1.89% | NIC / Diagnostic
#4 | FW update fail | 60 | 1.64% | Firmware
#5 | CX8 Fail | 60 | 1.64% | NIC / Diagnostic
#6 | GB200 GPU Burn Test fail | 58 | 1.59% | GPU
#7 | MFG Fail | 42 | 1.15% | Manufacturing
#8 | Sensor Missing | 37 | 1.01% | Sensor
#9 | auto reboot | 25 | 0.68% | Stability
#10 | Pending for final judgment (待最後判定) | 21 | 0.57% | Pending Judgment
| TOP 10 SUBTOTAL | 774 | 21.19%
▌ Top 3 Defect Reason Analysis
#1 — GB200 NVIDIA Manufacturer Diagnostic CX7/CX8 fail
Count: 332 (9.09%) — Single largest failure category. NVIDIA CX7/CX8 IB NIC diagnostic consistently fails during system-level test. Root cause likely: NIC firmware version mismatch, faulty CX8 connector seating, or transceiver compatibility. Requires NVIDIA engineering engagement. Action: Escalate to NVIDIA, check firmware compatibility matrix, audit CX8 installation torque spec.
#2 — GB200 Firmware flash Power failed on turn ON after 3 attempts
Count: 70 (1.92%) — Firmware flash failure during power cycling. Often caused by PSU instability during flash sequence, BMC communication timeout, or bad flash media. Action: Review PSU sequencing firmware, increase retry timeout, implement pre-flash PSU voltage check.
#3 — GPU Manufacturer Diagnostic - [FAILED]
Count: 69 (1.89%) — GPU-level diagnostic failure. Correlated with high GPU-NVGB300-12-MAXQ replacement rate (302 units). Possible causes: DOA GPU units, cooling issue affecting diagnostic, or corrupted diagnostic tool. Action: Cross-reference with GPU replacement records, coordinate with NVIDIA on GPU batch quality.
▌ Current PENDING Issues (Action=PENDING, as of Apr 23, 2026)
# | Error Date | Description | Defect P/N | Action
1 | 4/23/2026 | Error: Failed to set EGM to true. | CSE-MG104TS-R000NDP | PENDING
2 | 4/23/2026 | MFG Diagnostic Network test - [FAILED] | CSE-MG104TS-R000NDP | PENDING
3 | 4/23/2026 | AUTO REBOOT | CSE-MG104TS-R000NDP | PENDING
4 | 4/23/2026 | IPMI Sensor Check Failed | CSE-MG104TS-R000NDP | PENDING
5 | 4/23/2026 | Auto shutdown in Run In (?????????) | CSE-MG104TS-R000NDP | PENDING

## D - Replace Part TOP10
D. TI036 L10 Replacement Part TOP 10 Pareto
Total Replacement Events: 1,051 ¦ Period: Feb ~ Apr 2026 ¦ Source: TI036 Internal Defect Chart
Rank | Replace Component | Fail Q'ty | Weight % | Last 7 Days Qty
#1 | GPU-NVGB300-12-MAXQ | 302 | 28.73% | 27
#2 | AOM-PDB-B3-P | 129 | 12.27% | 11
#3 | AOC-CX8C8280U-GB | 95 | 9.04% | 2
#4 | AOM-OSFP-GB-P | 89 | 8.47% | 5
#5 | AOM-SCM-GB-P | 82 | 7.80% | 2
#6 | AOM-IO-GB-P | 58 | 5.52% | —
#7 | AOM-GBHMC | 36 | 3.43% | 4
#8 | GPU-NVDPU-BA3240-C-CA | 28 | 2.66% | 1
#9 | LCS-SLCM-N0028 | 26 | 2.47% | 3
#10 | HDS-MMN-MTFDKBG960TFR-15 | 26 | 2.47% | 3
| TOP 10 SUBTOTAL | 871 | 82.87% | 58
▌ Main Replacement Driver Analysis
► PRIMARY DRIVER: GPU-NVGB300-12-MAXQ
302 events (28.73%) — #1 replacement part by far. 43 replacements in last 7 days shows this is an ONGOING issue. GB300 GPU (NVIDIA GB300 SXM5) failures are driving the majority of L10 test failures. Key issues: GPU Manufacturer Diagnostic fail, GPU missing detection. Correlation with NDF data: marked "NA" — no confirmed NDF data available, suggesting actual GPU hardware defects.
► SECONDARY DRIVER: AOM-PDB-B3-P (Power Distribution Board)
129 events (12.27%) — #2 most replaced part. Power Distribution Board failures may be linked to power sequencing issues, transient surge damage, or upstream PSU problems. NDF Rate: 10.85% (14/129) — some units are NDF, suggesting sensitivity to testing conditions.
► TERTIARY DRIVER: AOC-CX8C8280U-GB (ConnectX-8 Adapter)
95 events (9.04%) — Highly correlated with the #1 fail reason (CX7/CX8 Diagnostic). CX8 adapters failing diagnostic and being replaced. Only 2 in last 7 days suggests possible improvement or batch change. NDF data: NA — requires investigation.
► L11 RACK DRIVER: GB300 L10 Node (rack-level)
332 of 437 L11 rack-level replacements (75.97%) are L10 full-node replacements. This means 57.7% of processed TI036 racks required at least one L10 node swap — a major yield impact at the system integration level.

## E - NDF Rate
E. TI036 L10 Replacement NDF Rate Analysis
NDF = No Defect Found ¦ #VALUE! in original Excel → recalculated ¦ NA/-: No return data
Rank | Replace Component | Fail Q'ty | Q'ty of NDF | NDF % | Data Status / Note
#1 | GPU-NVGB300-12-MAXQ | 302 | NA | nan% | NA – No Return/Confirm Data
#2 | AOM-PDB-B3-P | 129 | 14 | 10.85% | Confirmed NDF: 14
#3 | AOC-CX8C8280U-GB | 95 | NA | nan% | NA – No Return/Confirm Data
#4 | AOM-OSFP-GB-P | 89 | 6 | 6.74% | Confirmed NDF: 6
#5 | AOM-SCM-GB-P | 82 | 16 | 19.51% | Confirmed NDF: 16
#6 | AOM-IO-GB-P | 58 | 1 | 1.72% | Confirmed NDF: 1
#7 | AOM-GBHMC | 36 | - | nan% | NA – No Return/Confirm Data
#8 | GPU-NVDPU-BA3240-C-CA | 28 | - | nan% | NA – No Return/Confirm Data
#9 | LCS-SLCM-N0028 | 26 | - | nan% | NA – No Return/Confirm Data
#10 | HDS-MMN-MTFDKBG960TFR-15 | 26 | - | nan% | NA – No Return/Confirm Data
#11 | LCS-SLCM-N0027 | 18 | - | nan% | NA – No Return/Confirm Data
#12 | AOM-POSER-GB-P | 17 | 2 | 11.76% | Confirmed NDF: 2
#13 | CBL-ASMC-1455CM5YRF2P-X | 14 | 1 | 7.14% | Confirmed NDF: 1
#14 | AOC-PG-I1-P | 13 | 1 | 7.69% | Confirmed NDF: 1
#15 | CBL-PWEX-BB03Y-58 | 13 | - | nan% | NA – No Return/Confirm Data
▌ NDF Rate Key Findings
🔴 Highest NDF Rate: AOM-SCM-GB-P (19.51%)
16 out of 82 replacements returned No Defect Found. Likely cause: false failure detection or ESD damage during removal. Recommend: review test threshold, improve ESD protocol, implement cool-down retry before replacement.
🟡 Notable NDF: AOM-PDB-B3-P (10.85%) ¦ AOM-POSER-GB-P (11.76%) ¦ CBL-CDAT-1121-21 (20.00%)
Multiple parts with elevated NDF rates suggest over-aggressive replacement decisions. Implement mandatory re-test protocol before replacement for these components.
⚫ NA Data: GPU-NVGB300-12-MAXQ, AOC-CX8C8280U-GB, AOM-GBHMC, GPU-NVDPU (302+95+36+28 events)
Highest-volume parts have NO NDF tracking. #VALUE! errors in original Excel = text "NA"/"-" in NDF Qty cell. Fix: =IFERROR(NDF/Fail*100,"N/A"). Action: Implement NDF tracking for all top-10 parts immediately.
⚠️ LCS-SCDM-002WD004: NDF Rate 25.00% (1/4)
Small sample (n=4) — statistically inconclusive, but highest calculated NDF%. Monitor.

## F - Workmanship TOP10
F. TI036 L10 Workmanship Analysis – TOP 10 Root Causes
Total Workmanship Events: 218 ¦ Workmanship Rate: 1.62% (vs 13,438 L10 tested) ¦ Source: TI036 Workmanship Sheet
Rank | Workmanship Root Cause (Error Description) | Fail Q'ty | Weight % | AS-Code
#1 | COMPONENT DAMAGE (零件損壞_組裝責) | 114 | 52.29% | AS008
#2 | COMPONENT DAMAGE (零件損壞_測試責) | 22 | 10.09% | AS009
#3 | COMPONENT DAMAGE (零件損壞_維修責) | 19 | 8.72% | AS010
#4 | Not installed properly (未安裝定位) | 16 | 7.34% | AS013
#5 | COMPONENT DAMAGE (零件損壞_其它責) | 13 | 5.96% | AS012
#6 | WRONG LOCATE INSTALLATION (錯誤的安裝位置) | 5 | 2.29% | AS005
#7 | Screws not tightened or missing screws (螺絲沒鎖好或螺絲漏鎖) | 5 | 2.29% | AS018
#8 | Missing install (未安裝/漏裝) | 5 | 2.29% | AS014
#9 | COMPONENT DAMAGE (零件損壞) | 4 | 1.83% | AS001
#10 | Connector / Cable Bent pin | 4 | 1.83% | AS016
| TOP 10 SUBTOTAL | 207 | 94.95%
▌ Workmanship Root Cause Analysis
🔴 #1 ROOT CAUSE: AS008 – Component Damage (Assembly Responsibility) = 114 events (52.3%)
More than HALF of all workmanship defects are caused by component damage during assembly. Assembly staff are physically damaging parts (bent pins, scratched contacts, broken connectors) during installation. This is the single most critical workmanship control point. Top damaged parts: AOM-OSFP-GB-P (24 events), GPU-NVGB300-12-MAXQ (17 events), AOC-CX8C8280U-GB (9 events) Action: (1) Mandatory jig/fixture for OSFP and GPU installation; (2) ESD glove + connector protection protocol; (3) Video monitoring at high-risk assembly stations; (4) Technician certification refresh for AOM installation.
🟡 #2+#3: AS009+AS010 – Damage by Test/Repair Staff = 41 events (18.8%)
Test and repair personnel are also causing component damage during their work. 22 events (AS009, test responsibility) + 19 events (AS010, repair responsibility). Action: (1) Revised handling protocol for test setup/teardown; (2) MRB board oversight for AS009/AS010 incidents; (3) Implement "no-touch" zone marking on PCB for test probing.
🔵 #4: AS013 – Not Installed Properly = 16 events (7.3%)
Components installed incorrectly (wrong orientation, not fully seated). Common for connectors and cards. Action: Assembly SOP improvement with visual alignment guides; implement torque spec verification.
✅ Combined AS-Code Categories: COMPONENT DAMAGE dominates (70%+ of all workmanship)
AS001+AS008+AS009+AS010+AS012 = 172 events = 78.9% of all workmanship defects are "component damage" type. This strongly points to handling and assembly process improvement as the highest-ROI intervention. Separate root cause tracking by station/technician recommended.

## G - L11 Yield Data
G. GB300 L11 Yield Data – TI036 Rack-Level Component Replacement
L11 = Full rack system integration test ¦ Total Racks Processed: 575 ¦ Replace Events: 437
Rank | Part Description | Replace Component (P/N) | Fail Q'ty | Weight % | Impact on L11 Yield
#1 | GB300 L10 | PIO-121GL-NB3-LC5-TI036 | 332 | 75.97% | ⚠️ CRITICAL — 332 racks (57.7% of all racks) had L10 node swaps. #1 L11 yield driver
#2 | Cable Cartridge | SSE-NVL72-CC | 54 | 12.36% | 🔸 Cable Cartridge failures — impacts NVLink connectivity between L10 nodes
#3 | NVSwitch | SSE-NVL72SW-N5500 | 35 | 8.01% | 🔸 NVSwitch failures — impacts NVLink fabric switching; systemic if batch issue
#4 | power shelf left input | SRK-01LNPF-33B1-01 | 6 | 1.37% | 📋 Power shelf left input — minor; likely power transient sensitivity
#5 | Power shelf control module | SRK-01LNPM-PMB1-01-TI036 | 5 | 1.14% | 📋 Power shelf control module — affects power monitoring/management
#6 | 5.5kW PSU GB300 | SRK-01LNPW-5KB1-01-TI036 | 4 | 0.92% | 📋 5.5kW PSU — PSU failure; verify incoming inspection
#7 | LiteOn Power Shelf Right Input | SRK-01LNPF-33B1R-01 | 1 | 0.23% | 📋 LiteOn power shelf right input — single occurrence; monitor
| TOTAL | — | 437 | 100.00%
▌ L11 Yield Analysis – Component Impact Assessment
🔴 GB300 L10 Node (PIO-121GL-NB3-LC5-TI036): DOMINANT L11 Yield Killer
332 out of 437 rack-level replacements (75.97%) are GB300 L10 nodes. This means 57.7% of processed TI036 racks required at least one L10 swap. The L11 rack pass rate of 99.83% is despite these swaps — meaning replacement nodes eventually resolved the issues. However, the high swap rate adds significant rework time, cost, and spare parts consumption. Root cause cross-reference: L10 GPU fail (GPU-NVGB300-12-MAXQ), NIC fail (CX7/CX8), and power issues are the underlying drivers. Improving L10 incoming quality and L10-level FPY will directly reduce L11 L10 replacement rate.
🔵 Cable Cartridge (SSE-NVL72-CC): #2 L11 Driver — NVLink Interconnect Risk
54 replacements (12.36%). Cable Cartridges are the high-density NVLink fiber cables connecting GB300 nodes. Failures here impact GPU-to-GPU communication across the rack. Cable damage may occur during rack assembly or from repeated handling during L10 node swaps. Recommendation: Inspect Cable Cartridges whenever an L10 node is swapped; add post-L10-swap Cable Cartridge verification step.
🟢 NVSwitch (SSE-NVL72SW-N5500): #3 — Fabric-Level Impact
35 replacements (8.01%). NVSwitch failures cause NVLink fabric issues detectable during diagnostic. If multiple switches fail in a batch, it could indicate a firmware or batch quality issue. Recommend: Track NVSwitch firmware version at failure; check for batch correlation.
📊 Key Conclusion: L10 Node Quality → L11 Yield Chain
The L11 yield chain is: L10 quality (77.24% FPY) → L10 node replacement at L11 (332 events, 57.7% rack rate) → Cable Cartridge/NVSwitch secondary replacements (89 events) → L11 system pass (99.83%). Improving L10 FPY to >90% would reduce L11 L10 replacement rate by an estimated 50%+ and improve overall L11 throughput significantly.

## H - Charts Dashboard
H. Quality Analysis Charts Dashboard
Chart 1: TI036 L11 Yield Trend | Chart 7: TI036 L10 Daily Yield Trend
Chart 2: L10 FR Distribution & Action | Chart 3: Replacement Part TOP10 Pareto
Chart 4: NDF Rate Analysis | Chart 5: Workmanship Root Cause Pareto
Chart 6: L11 Component Impact | Chart 8: All Projects L11 Dashboard

## I - English Summary
I. Business Summary – English Version (Report Ready)
GB300 / TI036 Quality & Yield Report ¦ Period: Oct 21, 2025 – Apr 23, 2026
[ Directly paste the block below into your PowerPoint / Word report ]
───────────────────────────────────────────────────────────────────────────────── EXECUTIVE SUMMARY ───────────────────────────────────────────────────────────────────────────────── This report covers the quality and yield performance of the GB300 / TI036 program (NVL72 rack system) from October 21, 2025 to April 23, 2026. OVERALL ASSESSMENT: IMPROVING — L11 rack-level integration is near completion at 99.82% pass rate across all projects. L10 server-level first-pass yield stands at 77.24%, with active improvement efforts required. ───────────────────────────────────────────────────────────────────────────────── A. L11 UPDATE SUMMARY ───────────────────────────────────────────────────────────────────────────────── • TI036 (SRS-52UGB300-NVL72-TI036): - Cumulative L11 Input: 576 racks ¦ Pass: 575 racks ¦ Fail/Pending: 1 - L11 Pass Rate: 99.83% (575 / 576) - Total REPLACE events: 437 ¦ L10 node replacements: 332 (57.74% of racks) • All Projects Combined: xAI_TW008: 600/600 (100.00%) ✓ Complete TI036: 575/576 (99.83%) ● Active FG001: 256/256 (100.00%) ✓ Complete MA023: 190/192 (98.96%) ● Active TD004: 8/8 (100.00%) ✓ Complete ───────────────────────────────── TOTAL: 1,629/1,632 (99.82%) ───────────────────────────────────────────────────────────────────────────────── B. TI036 / GB300 L10 FAILURE RATE DISTRIBUTION ───────────────────────────────────────────────────────────────────────────────── Total Tested (L10 Server): 13,438 units Cumulative Pass (L10 FG): 10,379 units Total Failed: 3,059 units ────────────────────────────────────────────────── L10 Failure Rate (FR): 22.76% [3,059 / 13,438] L10 First Pass Yield Rate (FPY): 77.24% [10,379 / 13,438] Replacement SN Failure Rate (L11): 57.74% [332 L10 replacements / 575 racks] Workmanship Qty: 218 events Workmanship Rate: 1.62% [218 / 13,438] ───────────────────────────────────────────────────────────────────────────────── C. PENDING ISSUE TOP 10 — TI036 L10 (Feb ~ Apr 2026) ───────────────────────────────────────────────────────────────────────────────── Rank Defect Reason Qty Weight% ──── ──────────────────────────────────────────────────────── ───── ──────── #1 GB200 NVIDIA Mfr. Diagnostic CX7/CX8 fail 332 9.09% #2 GB200 Firmware flash Power failed (3 attempts) 70 1.92% #3 GPU Manufacturer Diagnostic [FAILED] 69 1.89% #4 FW update fail 60 1.64% #5 CX8 Fail 60 1.64% #6 GB200 GPU Burn Test fail 58 1.59% #7 MFG Fail 42 1.15% #8 Sensor Missing 37 1.01% #9 Auto reboot 25 0.68% #10 Pending for final judgment (待最後判定) 21 0.57% ──── ──────────────────────────────────────────────────────── ───── ──────── TOP 10 SUBTOTAL 774 21.19% ★ Key Insight: CX7/CX8 diagnostic failure (#1) is systemic and requires NVIDIA engineering engagement. GPU diagnostic failure (#3) correlates with high GPU replacement volume (302 events). ───────────────────────────────────────────────────────────────────────────────── D. REPLACEMENT PART TOP 10 — TI036 L10 ───────────────────────────────────────────────────────────────────────────────── Rank Replace Component Fail Q'ty Weight% Last 7 Days ──── ────────────────────────────── ───────── ─────── ─────────── #1 GPU-NVGB300-12-MAXQ (GB300 GPU) 302 28.73% 27 #2 AOM-PDB-B3-P (Power Dist. Board) 129 12.27% 11 #3 AOC-CX8C8280U-GB (CX8 NIC) 95 9.04% 2 #4 AOM-OSFP-GB-P (OSFP Module) 89 8.47% 5 #5 AOM-SCM-GB-P (SCM Card) 82 7.80% 2 #6 AOM-IO-GB-P (I/O Board) 58 5.52% — #7 AOM-GBHMC (HMC Module) 36 3.43% 4 #8 GPU-NVDPU-BA3240-C-CA (DPU) 28 2.66% 1 #9 LCS-SLCM-N0028 (Liquid Cooling) 26 2.47% 3 #10 HDS-MMN-MTFDKBG960TFR-15 (SSD) 26 2.47% 3 ──── ────────────────────────────── ───────── ─────── ─────────── TOP 10 SUBTOTAL 771 73.36% GRAND TOTAL 1,051 100.00% ★ GPU-NVGB300-12-MAXQ (#1) with 27 replacements in last 7 days = ongoing surge. Immediate vendor quality escalation recommended. ───────────────────────────────────────────────────────────────────────────────── E. REPLACEMENT NDF RATE — TI036 L10 ───────────────────────────────────────────────────────────────────────────────── Replace Component Fail Q'ty Q'ty NDF NDF% Note ────────────────────────────── ───────── ──────── ────── ────────────────── GPU-NVGB300-12-MAXQ 302 NA N/A No return data tracked AOM-PDB-B3-P 129 14 10.85% Over-replacement suspected AOC-CX8C8280U-GB 95 NA N/A No return data tracked AOM-OSFP-GB-P 89 6 6.74% Moderate NDF AOM-SCM-GB-P 82 16 19.51% ⚠️ HIGHEST NDF — review test criteria AOM-IO-GB-P 58 1 1.72% Low NDF AOM-GBHMC 36 - N/A Dash in source = no data GPU-NVDPU-BA3240-C-CA 28 - N/A Dash in source = no data LCS-SLCM-N0028 26 - N/A No return data AOM-POSER-GB-P 17 2 11.76% Elevated NDF Note: #VALUE! errors in original Excel = text "NA"/"-" in NDF Qty cell. Correction applied: NDF% = NDF_Qty / Fail_Qty × 100; text values → displayed as N/A. ───────────────────────────────────────────────────────────────────────────────── F. WORKMANSHIP TOP 10 — TI036 L10 ───────────────────────────────────────────────────────────────────────────────── Rank Workmanship Root Cause Qty Weight% Code ──── ───────────────────────────────────────────────── ──── ────── ───── #1 Component Damage – Assembly Responsibility 114 52.29% AS008 #2 Component Damage – Test Responsibility 22 10.09% AS009 #3 Component Damage – Repair Responsibility 19 8.72% AS010 #4 Not Installed Properly 16 7.34% AS013 #5 Component Damage – Other Responsibility 13 5.96% AS012 #6 Wrong Locate Installation 5 2.29% AS005 #7 Screws Not Tightened / Missing 5 2.29% AS018 #8 Missing Install (未安裝/漏裝) 5 2.29% AS014 #9 Component Damage (General) 4 1.83% AS001 #10 Connector / Cable Bent Pin 4 1.83% AS016 ──── ───────────────────────────────────────────────── ──── ────── ───── TOTAL 218 100.00% ★ Component Damage (AS008+AS009+AS010+AS001) = 159 events = 72.9% of all workmanship defects. Primary focus: assembly handling improvement. ───────────────────────────────────────────────────────────────────────────────── G. GB300 L11 YIELD DATA — COMPONENT IMPACT (TI036 RACKS) ───────────────────────────────────────────────────────────────────────────────── Part Description Replace Component Fail Q'ty Weight% ──────────────────────────── ──────────────────────────── ───────── ─────── GB300 L10 (Node) PIO-121GL-NB3-LC5-TI036 332 75.97% Cable Cartridge SSE-NVL72-CC 54 12.36% NVSwitch SSE-NVL72SW-N5500 35 8.01% Power Shelf Left Input SRK-01LNPF-33B1-01 6 1.37% Power Shelf Control Module SRK-01LNPM-PMB1-01-TI036 5 1.14% 5.5kW PSU GB300 SRK-01LNPW-5KB1-01-TI036 4 0.92% LiteOn Power Shelf Right SRK-01LNPF-33B1R-01 1 0.23% ──────────────────────────── ──────────────────────────── ───────── ─────── TOTAL 437 100.00% ★ GB300 L10 node replacement accounts for 75.97% of all L11 replacements. ★ The GB300 L10 node is the primary driver of L11 yield variability. ★ Improving L10 FPY (currently 77.24%) will have the highest positive impact on L11 throughput and rack-level quality. ───────────────────────────────────────────────────────────────────────────────── MANAGEMENT SUMMARY — RISK & RECOMMENDATIONS ───────────────────────────────────────────────────────────────────────────────── CURRENT STATUS: IMPROVING (L11 near completion, L10 FPY recovering) RISK LEVEL: MEDIUM-HIGH • GPU replacement surge (43 in last 7 days) — ACTIVE RISK • CX7/CX8 systemic failure — ONGOING • 5 PENDING items unresolved as of Apr 23, 2026 • High NDF rate for AOM-SCM-GB-P (19.51%) — cost/efficiency risk TOP 3 IMMEDIATE ACTIONS: P1. Escalate GPU-NVGB300-12-MAXQ to vendor — surge in last 7 days unacceptable P2. Root cause analysis with NVIDIA for CX7/CX8 diagnostic failure pattern P3. Clear 5 PENDING records before next batch shipment SHORT-TERM COUNTERMEASURES (1–4 weeks): • Implement NDF tracking for top-10 replacement parts (currently not tracked for GPU/CX8) • Add "cool-down retry" protocol before triggering replacement for AOM-SCM, AOM-PDB • Mandatory Cable Cartridge inspection after any L10 node swap LONG-TERM COUNTERMEASURES (1–3 months): • Assembly workmanship improvement program: jig/fixture for OSFP/GPU installation, ESD protocol refresh, technician re-certification • L10 FPY improvement target: raise from 77.24% to >88% — will reduce L11 L10 swap rate from 57.74% to estimated <30% • Implement per-batch quality tracking for GPU, CX8, and NVSwitch to detect incoming quality shifts early